## Readme
Troubleshoot Playbook
When doing upgrades, there may be some situations when the upgrades fails or the Bravura Security Fabric product is not working properly or performing slow after an upgrade.
This playbook covers procedures on how to collect debug information in order to understand causes of the issues and potentially resolve them
Common causes of upgrade failures include:
windows service control manager or mssql studio open when upgrade is launched.
Bravura Fabric procduct services are not properly shutdown before upgrade is launched.
Replication queues are not empty in a replicated environment
Network issues interrupting upgrade process
Web UI is not working properly after upgrade finished
This playbook is intended to outline the step-by-step process of how to collect logs and process dumps in an environment safely.
This playbook is a:
starting template to modify with your organization's specific needs
checklist to prevent forgetting steps or running them out of order
record of logs collected with timestamps
This playbook is not a:
replacement of the core docs, which should also be reviewed before upgrading Bravura Fabric Instance
How to
1 | Review this playbook
Action status legend:
|  |  | fail | Step failed or could not be completed
|  |  | not required | Not required for this step on this node
|  |  | partial pass | Step passed but with minor issues or unexpected behavior
|  |  | pass | Step passed without issue
|  |  | skipped | Step can be skipped for this step on this node, add note as required
|  |  | for review | Review if this step is applicable to your organization and add any notes and/or details as required
|  |  | to be completed | Step needs to be completed
|  |  | optional | Step is optional
|  |  | n/a | This is not applicable
2 | Duplicate the "Troubleshooting" sheet (to keep an original playbook), and modify the playbook copy for your specific use (rename it with the data and environment details where applicable)
| 2.1 | Update the node headings with your node IDs
| 2.2 | Add new columns for each additional node required beyond 3
| 2.3 | Include other specifics of your organization's setup, maintenance window and so on
|  | 2.3.1 | For rows marked as "for review", determine if they need to be completed, modify or marked with a different status (such as "to be completed" or "n/a").
|  | 2.3.2 | At your own risk, add new rows with steps to capture your organization's process requirements not otherwise included in this playbook.
Be careful that actions in new rows do not conflict with existing rows of the playbook.
|  | Note | Do not delete or hide any rows (except for hiding nodes you're not using).
Instead use the status fields and/or add notes.
3 | Duplicate your modified tab, run through the modified playbook in a test environment, and adjust as required
4 | Duplicate modified tab with any adjustments, perform troubleshooting
5 | Fill in all columns of the sheet as you go through them (including timestamps and notes)
| 5.1 | Take appropriate notes as each step is completed
| 5.2 | For partial passes take notes as to what was unexpected and why it is still considered a pass
| 5.3 | If a step fails collect logs, record the current state (including product, environment and database) and snapshot if possible. This information will be required for troubleshooting.
Additional notes
Each line should be completed for all nodes before proceeding to the next line.
Do not delete any rows from the playbook, instead mark as "n/a" or such as applicable.
Playbook details
Playbook last reviewed | Reviewer | Versions verified | Tester | Release notes
2023-06-09
Use this playbook to gather debugging information such as log gathering, gathering stored procedures plans, get memory dumps:
1 | Setup Debug Level Logging
2 | Collect Logs
3 | Gather system resources
4 | Collect SQL stored procedure plans
5 | Collect process memory dumps
6 | Collect leaky process dumps
Use Cases:
Below are few upgrade issues we have encountered previously. Follow one of the links below to proceed to the next step:
UC1 | Disrupted installation
UC2 | Upgrade fail on replica node
UC3 | Upgrade behaves as fresh instal
UC4 | WebUI doesn’t work after upgrade
UC5 | Migrated SQL Server databases

## Troubleshooting
Prod environment
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Setup Debug Level Logging | Globally using the administrative web interface: | Login as superuser. | n/a | to be completed | to be completed | to be completed
|  | Go to Manage the system -> Maintenance -> Services -> Bravura Security (idmlogsvc) Logging Service | n/a | to be completed | to be completed | to be completed
|  | Click Default level for log messages drop down and select one of the options: 1. No debugging (or in some versions No debug loggng): Reduces the logging to 0. Nothing gets logged, not even Critical, Errors or Warnings events 2. Default debugging: Logs errors, warnings, notices, and information messages 3. Full debugging: Logs all the messages in default logging and debugging information for the program | n/a | to be completed | to be completed | to be completed
|  | Click Enabled extended log levels and select extended log levels. It can be set to none, one or all of: 1. Runtime performance messages – All binary and script performance are recorded. 2. Ajax runtime performance messages – All Ajax requests, including the function name, transid, duration, and user are recorded. 3. Stored procedure runtime performance messages – The performance of stored procedures, called by binaries, is recorded. 4. Local workstation service runtime performance messages 5. Replication runtime performance messages – The performance of replication queues, stored procedures, is recorded. | n/a | to be completed | to be completed | to be completed
|  | Stop the Bravura Security (idmlogsvc) Logging Service. | n/a | to be completed | to be completed | to be completed
|  | Start the Bravura Security (idmlogsvc) Logging Service. | n/a | to be completed | to be completed | to be completed
| Using psdebug program: | Using Command Line Interface, navigate to instance util directory on Bravura Security Fabric. | n/a | to be completed | to be completed | to be completed
|  | psdebug can be called with the -h command-line option, in order to ask for the available options when using that executable. | n/a | to be completed | to be completed | to be completed
Example:
|  | Run "psdebug -prog <binary-or-script-without-extension> -level <newLevel> -extlevel <list of space-separates extlevels>" | n/a | to be completed | to be completed | to be completed
|  | where logging levels can be: | n/a | to be completed | to be completed | to be completed
|  | a. 1 - Log errors only | n/a | to be completed | to be completed | to be completed
|  | b. 2 - Log errors and warnings | n/a | to be completed | to be completed | to be completed
|  | c. 3 - Log errors, warnings, and notices | n/a | to be completed | to be completed | to be completed
|  | d. 4 - Log errors, warnings, notices, and information messages (default) | n/a | to be completed | to be completed | to be completed
|  | e. 5 - Log all the above and debugging information for the program | n/a | to be completed | to be completed | to be completed
|  | f. 99 - Log all the above and verbose debugging information | n/a | to be completed | to be completed | to be completed
|  | And -extlevel can be: | n/a | to be completed | to be completed | to be completed
|  | a. perf: Runtime performance messages – All binary and script performance are recorded | n/a | to be completed | to be completed | to be completed
|  | b. perf_sproc: Stored procedure runtime performance messages – The performance of stored procedures, called by binaries, is recorded. | n/a | to be completed | to be completed | to be completed
|  | c. perf_replication: Database replication messages – The name and duration of replicated stored procedures is recorded, as well as the send queue in which they are | n/a | to be completed | to be completed | to be completed
|  | running. | n/a | to be completed | to be completed | to be completed
|  | d. perf_lws: Local workstation runtime performance messages – The name and duration of local workstation stored procedures is recorded. | n/a | to be completed | to be completed | to be completed
|  | e. perf_ajax: Ajax runtime performance messages – All Ajax requests, including the function name, transid, duration, and user are recorded. | n/a | to be completed | to be completed | to be completed
Locate and collect Logs
| Locate and collect setup logs | setup.log file is located in Bravura Security Fabric installer source folder | n/a | to be completed | to be completed | to be completed
| Locate and collect upgrade logs | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | to be completed | to be completed | to be completed
| Locate and collect idmsuite logs | Idmsuite.log files are located in <Bravura security fabric instance name>\Logs | n/a | to be completed | to be completed | to be completed
| Locate and collect logs from windows event viewer | To collect event viewer logs, Press Windows+r: Type: eventvwr.msc and press Enter On Event Viewer, Go to Windows Logs-> Applications. Right click Aplications-> Save All Events As… Save the file. | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
System resources |  |  | n/a | to be completed | to be completed | to be completed
| Storage (Disk space) | By default in replicated instances, our product is configured to stop replicating when the available disk space drops under 10% (it tries to send email warnings long before that, by default as soon as 60% disk space is used) | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
| Processing (RAM, CPU, handles, sockets) | To get available (free RAM), Run following command from command line interface with elevated privileges: 1. wmic os get freephysicalmemory /format:value where value could be table,list,csv,hform,htable or xml | n/a | to be completed | to be completed | to be completed
| To check for memory leaks in paging and non-paging RAM: | Run following command from command line interface with elevated privileges: 1. poolmon /n this writes a log of all memory tag entries and their RAM use at the time The output of that default Windows command can be loaded in a spreadsheet program and sorted descending by its 6th column (Bytes) to find the most leaky processes. 2. To monitor for a specific memory tag leak, run: poolmon /iTIsn | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
| CPU usage | To get CPU usage, run: wmic cpu get loadpercentage /format:value where value could be table,list,csv,hform,htable or xml | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
Gather sproc sql plans |  |  | n/a | to be completed | to be completed | to be completed
| Using the Plan Cache | Log in to SQL Server using the SQL Server Management Studio with an account that will require the VIEW SERVER STATE permission or you can use the sa account. | n/a | to be completed | to be completed | to be completed
|  | Identify the database name that the Bravura Security Fabric instance is using. Once you have connected, right click on your connection and click "New Query." | n/a | to be completed | to be completed | to be completed
|  | Prepared Queries: You will need to modify the following code in two ways 1. Replace <database name> with the name of the database used by your Bravura Security Fabric instance 2. Replace <proc name> with the name of the stored procedure you have been asked to retrieve an execution plan for: SELECT query_plan, usecounts FROM sys.dm_exec_cached_plans a CROSS APPLY sys.dm_exec_query_plan(a.plan_handle) b CROSS APPLY sys.dm_exec_sql_text(a.plan_handle) c WHERE objtype = 'Proc' AND b.dbid = DB_ID('<database name>') AND text LIKE '%<proc name>%' ORDER BY usecounts DESC 3. Paste the resulting code into the query pane in SSMS and press F5 to execute it. You may get multiple rows of results; this is fine. Note their values under the "usecounts" column and repeat the following steps to save each plan. 4. Click on the link in the output pane under query_plan 5. A new tab will open. On older versions of SSMS, the tab will contain XML data (pictured). Newer versions of SSMS will display a diagram. In either case, right click on the tab and select the "Save" option. | n/a | to be completed | to be completed | to be completed
|  | Ad Hoc Queries: You will need to modify the following code in two ways: 1 Replace <database name> with the name of the database used by your Bravura Security Fabric instance 2 Replace <proc name> with the name of the stored procedure you have been asked to retrieve an execution plan for SELECT query_plan, usecounts FROM sys.dm_exec_cached_plans a CROSS APPLY sys.dm_exec_query_plan(a.plan_handle) b CROSS APPLY sys.dm_exec_sql_text(a.plan_handle) c WHERE objtype = 'Prepared' AND EXISTS ( SELECT 1 FROM sys.dm_exec_plan_attributes(a.plan_handle) WHERE attribute = 'dbid' and value = DB_ID('<database name>') ) AND text LIKE '%HIDDEBUG:<proc name>:%' ORDER BY usecounts DESC 3 Paste the resulting code into the query pane in SSMS and press F5 to execute it. You may get multiple rows of results; this is fine. Note their values under the "usecounts" column and repeat the following steps to save each plan. 4 Click on the link in the output pane under query_plan. 5. A new tab will open. On older versions of SSMS, the tab will contain XML data (pictured). Newer versions of SSMS will display a diagram. In either case, right click on the tab and select the "Save" option. | n/a | to be completed | to be completed | to be completed
|  | If no plans were output, you will need to manually trigger the code path that produces the problem and repeat this section. Usually, you can manually trigger the required code path by simply following whatever steps are causing the problem you are observing in the Bravura Security application you are using. | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
| Generating a Temporary Execution Plan | Plans from the cache are always preferable to temporary plans because they reflect a plan that was actually used by SQL Server. You should only follow this section for prepared plans that you were not able to retrieve from the cache. 1 Paste the name of the stored procedure into the query pane in SSMS. If you are logged in as sa, prefix the stored procedure name with the database name and schema name, separated by periods, like this: database.schema.proc 2 Highlight the name and click the "Show estimated execution plan" button. 3. A diagram should appear at the bottom of the query pane. Right click anywhere inside the diagram and click "Save Execution Plan As..." 4. Select a location to save the file | n/a | to be completed | to be completed | to be completed
Collect memory dumps
| Using Task Manager | If automatic crash dumps are not feasible for any reason, any process memory can be dumped at any time while the process (like a service) is running: 1. Task Manager> Details> sort/scroll to find process and right-click on it> Create dump file. right-click on the respective line in Task Manager's Processes tab, choose "Create memory dump". | n/a | to be completed | to be completed | to be completed
| Automatic Memory Dumps | If you want to get a memdump just as a binary or service quits unexpectedly, autodumps can be configured. The best solution is automatic memory-dumps enabled as described here: | n/a | to be completed | to be completed | to be completed
|  | https://msdn.microsoft.com/en-us/library/bb787181(VS.85).aspx | n/a | to be completed | to be completed | to be completed
|  | (HKEY_LOCAL_MACHINE\SOFTWARE\Microsoft\Windows\Windows Error Reporting\LocalDumps) | n/a | to be completed | to be completed | to be completed
| Using Procdump | If you don't (or can't) have that (maybe because you can't reboot the server where you need to apply it, or your company's security rules don't allow reg modifications), please get the sysinternals tool procdump from here: | n/a | to be completed | to be completed | to be completed
|  | http://technet.microsoft.com/en-us/sysinternals/dd996900.aspx | n/a | to be completed | to be completed | to be completed
|  | and run it as such: | n/a | to be completed | to be completed | to be completed
|  | procdump64.exe -ma -e -o psa.exe | n/a | to be completed | to be completed | to be completed
or
procdump.exe -e -x . idtrack.exe -diffset latest
|  | (The dmp file will be in the folder where you ran the procdump command.) | n/a | to be completed | to be completed | to be completed
|  | the procdump command has to be run while the process is already running, so it's better for services and other long-running binaries. In the case of CGIs like psa (and if the sysinternals tools are not allowed on the Bravura Security Fabric servers), it's better to use Microsoft's automatic dump setup in the registry to get a full memory dump (option 2 above). | n/a | to be completed | to be completed | to be completed
|  | https://blogs.msdn.microsoft.com/carmelop/2012/11/03/what-is-a-processs-memory-dump/ | n/a | to be completed | to be completed | to be completed
Handling leaky processes
| Using umdh | Below are sample commands to create a umdh summary our developers can use to check for memory leaks (if service footprint grows in the GB ranges) | n/a | to be completed | to be completed | to be completed
|  | For example, on the ajax service: | n/a | to be completed | to be completed | to be completed
|  | Note that enabling debugging will lead to decreased performance while the gflags are set; you may want to do this in the test environment if you notice that the ajax service grows significantly over a week there as well. | n/a | to be completed | to be completed | to be completed
|  | umdh (user mode dump heap) allows you to take snapshots of a process's heap and compare snapshots. | n/a | to be completed | to be completed | to be completed
|  | - http://support.microsoft.com/kb/268343 | n/a | to be completed | to be completed | to be completed
|  | - http://msdn.microsoft.com/en-us/library/ff560206(VS.85).aspx | n/a | to be completed | to be completed | to be completed
|  | 0. Install the UMDH utility. This is included with windbg. | n/a | to be completed | to be completed | to be completed
|  | The UMDH utility is included with the Debugging Tools for Windows, which can be installed through the Windows SDK: https://developer.microsoft.com/en-us/windows/downloads/windows-10-sdk | n/a | to be completed | to be completed | to be completed
|  | Below are sample commands to create two umdh dumps: | n/a | to be completed | to be completed | to be completed
|  | 1. Enable the "stack backtrace" option for your application via gflags. | n/a | to be completed | to be completed | to be completed
|  | "C:\Program Files (x86)\Windows Kits\10\Debuggers\x64\gflags.exe" -i ajaxsvc.exe +ust | n/a | to be completed | to be completed | to be completed
|  | 2. Restart the ajax service and get it in a steady state (run a few idr pages, see if they are not too much slower, then use all other parts of the WebUI which normal users access). | n/a | to be completed | to be completed | to be completed
|  | 3. check Task Manager for the current processID (pid) of the service's image name: | n/a | to be completed | to be completed | to be completed
|  | 4. Generate the first capture: | n/a | to be completed | to be completed | to be completed
|  | "C:\Program Files (x86)\Windows Kits\10\Debuggers\x64\umdh.exe" -p:<pid> -g -f:dump_1_1.txt | n/a | to be completed | to be completed | to be completed
|  | Wait for a day, few days, a week and wait for its memory footprint to increase (and for the instance use to be as close to "idle" as possible). | n/a | to be completed | to be completed | to be completed
|  | 5. Generate the second capture: | n/a | to be completed | to be completed | to be completed
|  | "C:\Program Files (x86)\Windows Kits\10\Debuggers\x64\umdh.exe" -p:<pid> -g -f:dump_1_2.txt | n/a | to be completed | to be completed | to be completed
|  | 6. Disable gflags | n/a | to be completed | to be completed | to be completed
|  | "C:\Program Files (x86)\Windows Kits\10\Debuggers\x64\gflags.exe" -i <image name> -ust | n/a | to be completed | to be completed | to be completed
|  | 7. Restart the ajax service and verify that it's back at the "normal" rendering speed before enabling debugger. | n/a | to be completed | to be completed | to be completed

## UC1-Disrupted installation
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Issue | Open service control manager can disrupt installations and upgrades | The installer can malfunction when the Control Panel> Services manager is open. This can happen both for: 1. patching (increasing the build# of the instance, on the same version), AND 2. upgrading (increasing the version of the product without fresh install)
Environment |  | Product: Bravura Security Fabric, Bravura Pass, Bravura Identity, Bravura Privilege Earliest affected version: 12.0.0+
Setup debug level logging |  | Follow these steps on how to setup debug level logging
Steps to Reproduce Error/Issue | Run setup.exe to start upgrading | The installer can hit errors when it tries to add/remove services. These errors will fail upgrade, where the instance can roll back to a unstable state, which can make it difficult to uninstall the half-upgraded instance or try the upgrade again. Specific signs to look for are failures to add/remove services in the installer log, such as: MSI (s) (20:70) [21:43:14:390]: Invoking remote custom action. DLL: C:\Windows\Installer\MSIBE57.tmp, Entrypoint: UninstallIDMServices 1: Error uninstalling [iddiscover_<instancename>] service. Error 1060 : The specified service does not exist as an installed service. 1: Error uninstalling [idarch_<instancename>] service. Error 1060 : The specified service does not exist as an installed service. and then later: MSI (s) (20:08) [21:51:47:339]: Invoking remote custom action. DLL: C:\Windows\Installer\MSI921D.tmp, Entrypoint: InstallIDMServices 1: Install error: Service [idarch_<instancename>] already exists. 1: Install error: Service [iddiscover_<instancename>] already exists.
Collect Logs |  | Locate and collect logs
Collect System resources usage
| Storage (Disk space) | Follow steps here to gather Storage (Disk space), Processing (RAM, CPU, handles, sockets), Memory Leaks and CPU usage
Processing (RAM, CPU, handles, sockets)
Memory Leaks
CPU usage
Gather sproc sql plans | Using the Plan Cache | Follow these steps on how to gather stored procedure plans using plan cache
| Generating a Temporary Execution Plan | Follow these steps on how to gather temporary execution plan. This step is only needed if failed to get sql plan using plan cache.
Collect memory dumps | Using Task Manager | Follow these steps on how to collect memory dumps using task manager
| Automatic Memory Dumps | Follow these steps on how to collect memory dumps using through automatic memory dumps
| Using Procdump | Follow these steps on how to collect memory dumps using procdump
Collect leaking process dumps | Use umdh | Follow these steps on how to collect dumps from leaky processes
Resolution procedure | Mitigation | Once the upgrade has failed in this manner, the instance might not be uninstallable via setup, and we may need to manually remove whatever remains of the instance: From windows CLI, execute sc.exe delete *_<instancename> to remove any remaining service records In the Windows registry, HKLM\SOFTWARE\Microsoft\Windows\CurrentVersion\Uninstall, remove the product guid that matches the one present in HKLM\SOFTWARE\Bravura Security\Bravura Security Fabric If the upgrade does fail in this way, most likely it's failed after the backend database upgrade step has already completed (RunDBScripts will report in the installer log that it ran successfully). So at this point, we can then reinstall the new version. We'll want to get the server guid from iddb.cfg, and supply it to the installer as an additional MSI property, so the new instance has the same guid as the old one. e.g.: setup.exe -opts SERVER_GUID=7a65f4bc-bd8e-4dc6-89f5-280756ec0b30 Placing the old instance's psconfig\idmsetup.inf in the same directory as setup.exe before running it, can ensure the other instance details are the same as what was present previously. | n/a | to be completed | to be completed | to be completed
Solution |  | Ensure that the windows service control manager is closed before running our installers. If you do have the Services control manager open when patching/upgrading and this happens, you will need to follow the steps above to recover.

## UC2-Upgrade fail on replica
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Issue | Upgrade fails on replicated node(s) | When using setup to perform an upgrade on a replicated node, you may get the message: "You did not provide a database name".
Environment |  | Product: Bravura Security Fabric, Bravura Pass, Bravura Identity, Bravura Privilege Earliest affected version: 11.1.0+
Setup debug level logging |  | Follow these steps on how to setup debug level logging
Steps to Reproduce Error/Issue | Run setup.exe to start upgrading | 1. Perform an upgrade via setup.exe on the primary node. This should work successfully. 2. Perform an upgrade via setup.exe on the secondary node. 3. If the issue is present, the message “You did not provide a database name” will be displayed and the upgrade will fail.
Collect Logs |  | Locate and collect logs
Collect System resources usage
| Storage (Disk space) | Follow steps here to gather Storage (Disk space), Processing (RAM, CPU, handles, sockets), Memory Leaks and CPU usage
Processing (RAM, CPU, handles, sockets)
Memory Leaks
CPU usage
Gather sproc sql plans | Using the Plan Cache | Follow these steps on how to gather stored procedure plans using plan cache
| Generating a Temporary Execution Plan | Follow these steps on how to gather temporary execution plan. This step is only needed if failed to get sql plan using plan cache.
Collect memory dumps | Using Task Manager | Follow these steps on how to collect memory dumps using task manager
| Automatic Memory Dumps | Follow these steps on how to collect memory dumps using through automatic memory dumps
| Using Procdump | Follow these steps on how to collect memory dumps using procdump
Collect leaking process dumps | Use umdh | Follow these steps on how to collect dumps from leaky processes
Resolution procedure | Mitigation | If upgrading a Bravura Security Fabric version earlier than 10.1.1, ask Support for the patch On the affected node, make note of the following settings: 1. Under HKLM\SOFTWARE\Hitachi ID\IDM Suite\ the GUIDMask value
|  |  | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
|  |  | n/a | to be completed | to be completed | to be completed
2. Under HKLM\SOFTWARE\Hitachi ID\IDM Suite\Instance Name the GUIDMask value
The GUIDMask value (2) under the instance must match the first 9 characters, including the curly brace, of the GUIDMask value (1) found in the IDMSuite key. 3. If the values do not match, replace the GUIDMask values with the correct 9 characters and retry the upgrade.
Root Cause |  | The GUIDMask registry value is mismatched on replicated nodes.

## UC3-Upgrade behaves as fresh in
Prod environment
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Issue | Upgrade behaves as a fresh install | While upgrading an instance, the Bravura Security Fabric setup.exe installer thinks it is being given a new instance to install with the same name as the existing instance. This causes an error to appear in the dialog box saying, "This destination directory is already used by another instance. Please choose another."
Environment |  | Product: Bravura Security Fabric, Bravura Pass, Bravura Identity, Bravura Privilege Earliest affected version: 11.1.0+
Setup debug level logging |  | Follow these steps on how to setup debug level logging
Steps to Reproduce Error/Issue | Run setup.exe to start upgrading | Run the Bravura Security Fabric setup.exe installer. Select the instance. Click Upgrade. After proceeding with the upgrade, the installer throws an error saying it was given a new fresh instance to install with the same name as the existing instance.
Collect Logs |  | Locate and collect logs
Collect System resources usage
| Storage (Disk space) | Follow steps here to gather Storage (Disk space), Processing (RAM, CPU, handles, sockets), Memory Leaks and CPU usage
Processing (RAM, CPU, handles, sockets)
Memory Leaks
CPU usage
Gather sproc sql plans | Using the Plan Cache | Follow these steps on how to gather stored procedure plans using plan cache
| Generating a Temporary Execution Plan | Follow these steps on how to gather temporary execution plan. This step is only needed if failed to get sql plan using plan cache.
Collect memory dumps | Using Task Manager | Follow these steps on how to collect memory dumps using task manager
| Automatic Memory Dumps | Follow these steps on how to collect memory dumps using through automatic memory dumps
| Using Procdump | Follow these steps on how to collect memory dumps using procdump
Collect leaking process dumps | Use umdh | Follow these steps on how to collect dumps from leaky processes
Resolution procedure
| Verify Instance Details and Permissions | 1. Verify that there is a single instance of Bravura Security Fabric installed on the server.If there is more than one, do not continue and collect the installer log. Contact Bravura Security support with your environment details and provide the installer log for investigation. | n/a | to be completed | to be completed | to be completed
|  | 2. Make sure you ran setup.exe from an administrative account with elevated privileges. If you are running the setup.exe from a command prompt, ensure it is being run as an administrator. To do this: Open the Windows Start menu. type cmd. Right-click Command Prompt and select Run as administrator. | n/a | to be completed | to be completed | to be completed
|  | 3. If the permission issue was not the problem, there may be something wrong with the records in the Windows Installer database. This particular installer record could be an isolated issue or only the tip of the iceberg of a larger problem on the server. It is up to the customer product administrator as well as the pressures and time constraints of the upgrade/patch process whether to continue with this (fast) mitigation or to (slow but safe) restore/upgrade/reinstall the server OS to a fully working state. | n/a | to be completed | to be completed | to be completed

## UC4-WebUI issues after upgrade
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Issue | Browser shows as blank after upgrade | Upgrading Bravura Security Fabric produces a blank page when browsing to the application's main page.
Symptom |  | Upgrading from 10.0.0 to 12.0.3 produces a blank page when browsing to the application's main page.
Setup debug level logging |  | Follow these steps on how to setup debug level logging
Steps to Reproduce Error/Issue | Run setup.exe to start upgrading | 1. Perform an in-place upgrade for Bravura Security Fabric using the installer setup.exe. 2. Run the installer and finish the upgrade 3. When browsing to the login to Bravura Security Fabric page, a blank page shows up.
Collect Logs |  | Locate and collect logs
Collect System resources usage
| Storage (Disk space) | Follow steps here to gather Storage (Disk space), Processing (RAM, CPU, handles, sockets), Memory Leaks and CPU usage
Processing (RAM, CPU, handles, sockets)
Memory Leaks
CPU usage
Gather sproc sql plans | Using the Plan Cache | Follow these steps on how to gather stored procedure plans using plan cache
| Generating a Temporary Execution Plan | Follow these steps on how to gather temporary execution plan. This step is only needed if failed to get sql plan using plan cache.
Collect memory dumps | Using Task Manager | Follow these steps on how to collect memory dumps using task manager
| Automatic Memory Dumps | Follow these steps on how to collect memory dumps using through automatic memory dumps
| Using Procdump | Follow these steps on how to collect memory dumps using procdump
Collect leaking process dumps | Use umdh | Follow these steps on how to collect dumps from leaky processes
Resolution procedure |  | 1. Open the browser on the server where upgrade took place. 2. Open F12 Developer Tools on the browser. There will be a more detailed message that shows up, but only if you open the browser with Developer Tools on the server itself. In this case, the error message was '“Request Filtering” module blocked'. 3. The "network" will show a lot of 404 errors showing .js scripts that were blocked amongst other files that were blocked as well. 4. Allow the file extensions in IIS > Request Filtering module. Open IIS > Request Filtering and put in any missing file extensions that application requires. For example add in .exe, .js, .woff2, .jpg, etc.. Under "Allowed" column set it to "True. 5. Once the extensions have been added and browse the page again, the contents of the application should appear again. | n/a | to be completed | to be completed | to be completed

## UC5-Migrated SQL Server db
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Issue | Upgrade or patch fails when using migrated SQL Server databases | After migrating a Bravura Security Fabric product database from either SQL Server Standard Edition or Express Edition to Enterprise Edition, the product is no longer upgradable (in-place patches may fail due to schema mismatch).
Requirements | Pre-requisites to reproduce the problem | An existing installation of the application, using MS SQL Server (or a cluster thereof) The need to migrate to another database center or server engine Already checked that the new database version is supported by the application version Already checked that the new cluster configuration doesn't lock the database schema while replicating.
Setup debug level logging |  | Follow these steps on how to setup debug level logging
Steps to Reproduce Error/Issue | Run setup.exe to start upgrading | While executing setup.exe to upgrade or patch to a newer version, the upgrade process fails with an error similar to this: Invalid partition scheme ‘request_partscheme’ specified. Validating: If the above result is observed, Execute the following SQL query against the existing product SELECT * FROM [dbname].sys.partition_schemes WHERE name = 'request_partscheme' (substitute the appropriate database name for dbname in the query above) The above query should return no results (zero rows) only when running on SQL Server Standard Edition or Express Edition. If it also returns no results on SQL Server Enterprise Edition, the issue is present.
Collect Logs |  | Locate and collect logs
Collect System resources usage
| Storage (Disk space) | Follow steps here to gather Storage (Disk space), Processing (RAM, CPU, handles, sockets), Memory Leaks and CPU usage
Processing (RAM, CPU, handles, sockets)
Memory Leaks
CPU usage
Gather sproc sql plans | Using the Plan Cache | Follow these steps on how to gather stored procedure plans using plan cache
| Generating a Temporary Execution Plan | Follow these steps on how to gather temporary execution plan. This step is only needed if failed to get sql plan using plan cache.
Collect memory dumps | Using Task Manager | Follow these steps on how to collect memory dumps using task manager
| Automatic Memory Dumps | Follow these steps on how to collect memory dumps using through automatic memory dumps
| Using Procdump | Follow these steps on how to collect memory dumps using procdump
Collect leaking process dumps | Use umdh | Follow these steps on how to collect dumps from leaky processes
Resolution procedure |  | 1. Verify that the database migration is supported before proceeding with it 2. If the migration was performed previously and the original database is not available anymore or contains obsolete data, see Mitigation | n/a | to be completed | to be completed | to be completed
Mitigation |  | Post-installation migration between different SQL Server editions is not supported. Re-migrate the product database back to SQL Server Standard Edition or Express Edition. Alternatively, Bravura Security Professional Services may be engaged for a custom migration, if re-migration to the original edition is impossible.

## Hidden
Action status
fail
not required
partial pass
pass
skipped
for review
to be completed
optional
n/a