## Readme
Rolling upgrade Playbook
A rolling upgrade is where nodes are upgraded in sequence while ideally maintaining at least two nodes running in production. This is recommended to keep business disruptions to a minimum.
A rolling upgrade is appropriate for patch releases where no major product changes such as schema changes are made.
A rolling upgrade is *not* appropriate for major or minor upgrades, or where major product changes such as schema changes are made.
This playbook is intended to be a step-by-step guide to walk through a rolling upgrade systematically and safely.
This playbook is a:
starting template to modify with your organization's specific needs
checklist to prevent forgetting steps or running them out of order
record of decisions made both before and during upgrade
record of upgrade details, such as time taken on specific steps and outcomes
This playbook is not a:
replacement of the core docs, which should also be reviewed before upgrading
How to
1 | Review this playbook
Action status legend:
|  |  | fail | Step failed or could not be completed
|  |  | not required | Not required for this step on this node
|  |  | partial pass | Step passed but with minor issues or unexpected behavior
|  |  | pass | Step passed without issue
|  |  | skipped | Step can be skipped for this step on this node, add note as required
|  |  | for review | Review if this step is applicable to your organization and add any notes and/or details as required
|  |  | to be completed | Step needs to be completed
|  |  | optional | Step is optional
|  |  | n/a | This is not applicable
2 | Duplicate the "Rolling Upgrade Playbook - master" sheet (to keep an original playbook), and modify the playbook copy for your specific use (rename it with the data and environment details where applicable)
| 2.1 | Update the node headings with your node IDs
| 2.2 | Unhide relevant sections if you have more than 3 nodes
| 2.3 | Add new columns and sections if you have more than 6 nodes
| 2.4 | Primary node must be upgraded first, and completed before starting secondary nodes. We recommend keeping a minimum of two nodes running in production at all times. Assuming you have that, you can upgrade remaining nodes in parallel. If you want to do this, modify the playbook to reflect this.
| 2.5 | Include other specifics of your organization's setup, maintenance window and so on
|  | 2.5.1 | For rows marked as "for review", determine if they need to be completed, modify or marked with a different status (such as "to be completed" or "n/a").
|  | 2.5.2 | At your own risk, add new rows with steps to capture your organization's process requirements not included in this playbook.
Be careful that actions in new rows do not conflict with existing rows of the playbook.
|  | Note | Do not delete or hide any rows (except for hiding nodes you're not using).
Instead use the status fields and/or add notes.
3 | Duplicate your modified tab, run through the modified playbook in a test environment, and adjust as required
4 | Duplicate modified tab with any adjustments, upgrade production
5 | Fill in all columns of the sheet as you go through them (including timestamps and notes)
| 5.1 | Take appropriate notes as each step is completed
| 5.2 | For partial passes take notes as to what was unexpected and why it is still considered a pass
| 5.3 | If a step fails collect logs, record the current state (including product, environment and database) and snapshot if possible. This information will be required for troubleshooting.
Additional notes
Each line should be completed for all nodes before proceeding to the next line.
Do not delete any rows from the playbook, instead mark as "n/a" or such as applicable.
During the upgrading process, nodes are in one of three states - old version, upgrading and upgraded.
Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version.
Playbook details
Playbook last reviewed | Reviewer | Versions verified | Tester | Release notes
2022-07-25 | CF | Upgraded from 12.4.0.34189 to 12.4.0.34204 | CF | N/A
2022-11-24 | CF CT | N/A | N/A | N/A
2024-11-28 | CF | None | ML | Updates12.7 Upgrade
Note on C33: There are 6 nodes in the playbook sheet, 3 of them are hidden

## Rolling Upgrade Playbook - mast
|  | Starting Version | Upgrade Version |  | Notes
Bravura Fabric
Bravura Connector Pack
All nodes in each line should be completed before proceeding to the next line. That is, ensure each node for a step is completed or otherwise addressed (such as, "not required") before proceeding to the next step. |  |  |  | Prod environment
Stage | Step | Notes | Details | System/Environment | <Primary> | <Node 2> | <Node 3> | <Node 4> | <Node 5> | <Node 6> | Estimated time | Start time | End time | Notes
Preparation
| Create inventory of potentially affected systems |  | Have an inventory of potentially affected systems to determine the location of all Bravura Security Fabric components that need to be upgraded or migrated. A suggested list can be found here. | for review | not required | not required | not required | not required | not required | not required
| Create a test plan |  | Have a test plan that identifies use cases covering the required capability of the system. More details can be found here. | for review | not required | not required | not required | not required | not required | not required
| Verify os and sql server configuration |  | The windows operating system and database must be the same versions and configuration on all nodes. This step simply asks people to verify this is indeed the case. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Verify system requirements |  | System requirements can be found here: • python version • Microsoft OLE DB Driver for SQL Server • .NET Core Hosting Bundle 6.0.x and Desktop Runtime 6.0.x • Supported database management systems | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Verify product build version |  | Build version should match primary node's. Information for build version can be found here. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Check availability of database credentials |  | Need to make sure we have dba level access to all databases both to take backups and to apply the backups | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Check availability to database backup locations |  | Need to make sure suitable space exists to hold the database backups. More details can be found here. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Check ability to transfer database backups to secondary sites |  | Need to ensure its known how the database backups will be transferred between the nodes. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Check availability of Bravura Security Fabric credentials |  | Need to make sure we have access to the Bravura Security Fabric service user credentials. More details can be found here. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Review release notes |  | Assess their impact on your deployment. Release notes can be found here. | to be completed | not required | not required | not required | not required | not required | not required
| Check customizations |  | Confirm product customizations that will need to be ported. For example: • Scripts, plugins, and configuration files • Services • Reports • Product customizations and fixes • Web interface modifications • Language packs • Use "Instance customizations" report to discover customizations • Review previous changes to list all custom components | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Determine if you have any customer-verified connectors |  | This step only applies when upgrading to CP 4.6.0 or newer Bravura Security-verified and Customer-verified connectors are listed here. | n/a | for review | for review | for review | for review | for review | for review
| Determine if you have connectors that will be deprecated or removed during the Connector Pack upgrade |  | If you have connectors that are listed to be deprecated or removed please contact support. Removed connectors and replacements is listed here. | n/a | for review | for review | for review | for review | for review | for review
| Check out administrator access as required |  | Ensure access to <ADMIN> accounts | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Copy installation package to all servers |  | Verify correct package on each node | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Confirm correct upgrade process is triggered |  | Verify the following option is available: • Proceed with a rolling upgrade | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Ensure pre-upgrade checks pass on each node | Services are stopped during runtime install portion of the pre-upgrade checks. Recommended to run on each node sequentially to avoid downtime of the full environment | • Run setup • Select the products you want to upgrade • Bravura Security Fabric • Bravura Connector Pack 64-bit • Bravura Proxy Server • Ensure pre-upgrade tests pass • Cancel the installer | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Database upgrade dry run |  |  | This section is to walk through verifying the database upgrade can be completed smoothly.
| Create a back up of the Instance DB |  | The database upgrade test will be done against a copy of your database. This will help verify that the database can be upgraded without interferring with production. If errors occur during the database upgrade test they can be caught and handled before upgrading production. | n/a | for review | for review | for review | for review | for review | for review
| Create a Test DB |  | Recommended to be done on a different server. The following is for MSSQL: 1. Log into SQL Server as a DBA 2. In "Database" create a new database | n/a | for review | for review | for review | for review | for review | for review
| Apply database backup onto the Test DB |  | As DBA apply the database backup to the test database. Documentation on restoring SQL database can be found here. | n/a | for review | for review | for review | for review | for review | for review
| Create DBUser Login for the Test DB |  | The following is for MSSQL: • Log into SQL Server as a DBA • In “Security → Logins”, create a new user. If SQL Server Authentication is selected ensure the options User must change password at next login and Enforce password expiration are deselected. | n/a | for review | for review | for review | for review | for review | for review
| Give the DBUser permissions for the Test DB |  | The following is for MSSQL: Give the DBUser permissions on the Test DB • On SQL Server Management Studio, go to Security → Logins → right click the destination DBUser and select Properties. • On the General page ensure the test database is selected as "Default Database" • On the Server Roles page ensure the "public" server role is given. Ensure the "sysadmin" role is not given. • On the User mapping page ensure the user is mapped to the test database and the Default schema is set to the backed up schema. Check the following roles are given for the instance database: db_datareader, db_owner, db_datawriter, db_ddladmin, and public • On SQL Server Management Studio, go to Databases → (Test DB) → Users → right click the DBUser and select Properties. • On the Membership page verify the following roles are selected: db_datareader, db_owner, db_datawriter, and db_ddladmin | n/a | for review | for review | for review | for review | for review | for review
| Run upgradetest.exe |  | upgradetest.exe -db <TestDB> -s <Server> -u <DBUser> Ensure the upgradetest.exe is from the installation package you are upgrading to. | n/a | for review | for review | for review | for review | for review | for review
| Review results as needed |  | If there are any issues such as: • Failed upgrade scripts • Failed schema verification Please reach out to support. | n/a | for review | for review | for review | for review | for review | for review
Reducing sources of change
| Prepare custom component upgrade |  | Dependent on the specific customization. For example, this step may include running custom upgrade scripts, and/or removing custom components in favour of base product new features. | n/a | to be completed | not required | not required | not required | not required | not required
| Disable OTP randomization |  | To disable password randomization for all OTP API accounts, create a DWORD entry (DisableAllOTP) in the IDAPI directory of the instance registry key Set DisableAllOTP to 1 | n/a | for review | for review | for review | for review | for review | for review
| Enable RES_DISABLE_RANDOMIZATIONS_ALLOW_CHECKOUTS system variable |  | Enable this variable to allow check-outs while randomization is disabled. More details can be found here. Settings will be replicated to secondary nodes | n/a | to be completed | not required | not required | not required | not required | not required
| Disable all password randomizations in all policies |  | Setting found on the "Managed system policies" page. More details can be found here. Setting will be replicated to secondary nodes. | n/a | to be completed | not required | not required | not required | not required | not required
| Disable auto discovery |  | Navigate to Scheduled jobs. Select PSUPDATE and disable. | n/a | to be completed | not required | not required | not required | not required | not required
| Ensure auto discovery is complete |  | Ensure that auto discovery has finished running and is no longer running. Do not kill the processes if they are running and just allow to complete. | n/a | to be completed | not required | not required | not required | not required | not required
| Ensure no maintenance tasks scheduled on SQL nodes |  | Check with DBA to ensure that DB maintenance tasks, such as a DB reindex, will not be running during patching. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Disable Bravura Security Fabric Scheduled tasks in the OS Scheduler |  | Health checks, pwdconficts, etc. We need to ensure that pwdconflicts is not running until all nodes are operational otherwise it will identify a range of issues since the nodes are in a problematic state due to the database resynchronization being done. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Disable all schedule tasks related to Bravura Security Fabric services |  |  | n/a | for review | for review | for review | for review | for review | for review
Isolating <Primary>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from primary node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | Block all Bravura Security Fabric traffic to and from upgrading node. For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. | n/a | for review | for review | for review | for review | for review | for review
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See purple box) |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Primary>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | to be completed | not required | not required | not required | not required | not required
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | to be completed | not required | not required | not required | not required | not required
| Backup database on <Primary> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | to be completed | not required | not required | not required | not required | not required
| Add new custom components changes in this upgrade if any. |  | Add/remove update files as applicable. May need to uninstall previous custom components. Back up custom components if not already done. Do not load components after modifying at this time. The installer will complete this in the following step. | n/a | for review | not required | not required | not required | not required | not required
| Upgrade proxy servers. |  | • Run setup via installers • Ensure IIS is off on each node after proxy server upgrade | to be completed | not required | not required | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | for review | not required | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | for review | not required | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | for review | not required | not required | not required | not required | not required
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | to be completed | not required | not required | not required | not required | not required
| Manually rebuild skins if required |  | Required only if rebuild skins fail or has issues during post-upgrade tasks | n/a | for review | not required | not required | not required | not required | not required
| Manually reload connector pack if required |  | Required only if loading connectors fail or has issues during post-upgrade tasks | n/a | for review | not required | not required | not required | not required | not required
| Manually reload components if required |  | Required only if component initialization fails or has issues during upgrade on script\manage_components.p load --upgrade | n/a | for review | not required | not required | not required | not required | not required
| Remove IIS server access restrictions |  |  | n/a | to be completed | not required | not required | not required | not required | not required
Smoke tests on <Primary>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | to be completed | not required | not required | not required | not required | not required
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | to be completed | not required | not required | not required | not required | not required
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | to be completed | not required | not required | not required | not required | not required
| Verify requests to access a password - auto approved case |  |  | n/a | to be completed | not required | not required | not required | not required | not required
| Verify request to access a password - with authorization case |  |  | n/a | to be completed | not required | not required | not required | not required | not required
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | to be completed | not required | not required | not required | not required | not required
| Test connection to target systems |  |  | n/a | to be completed | not required | not required | not required | not required | not required
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | for review | not required | not required | not required | not required | not required
Adding back <Primary>
| Restore access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Start node upgrade
Isolating <Node 2>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from upgrading node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. This includes blocking all ports used by Bravura Security Fabric services. | n/a | for review | for review | for review | for review | for review | for review
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See blue and purple box). |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Node 2>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | not required | to be completed | not required | not required | not required | not required
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | not required | to be completed | not required | not required | not required | not required
| Backup database on <Node 2> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | not required | to be completed | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | not required | for review | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. |  | not required | for review | not required | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. |  | not required | for review | not required | not required | not required | not required
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Do not proceed to the Post-Upgrade Tasks page | n/a | not required | to be completed | not required | not required | not required | not required
| Remove firewall between <Primary> and <Node 2> | Firewalls should isolate upgraded nodes from non-upgraded/upgrading nodes (see Blue box) |  | n/a | for review | for review | not required | not required | not required | not required
| Complete Post-Upgrade Tasks |  | • Proceed to the Post-Upgrade Tasks • When complete remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | to be completed
| Manually rebuild skins if required |  | Required if rebuild skins fail or has issues during post-upgrade tasks | n/a | not required | for review | not required | not required | not required | not required
| Manually reload connector pack if required |  | Required if loading connectors fail or has issues during post-upgrade tasks Iddb required on the node this is ran on | n/a | not required | for review | not required | not required | not required | not required
| Manually reload components if required |  | Required if component initialization fails or has issues during upgrade script\manage_components.p load --upgrade Iddb required on the node this is ran on | n/a | not required | for review | not required | not required | not required | not required
| Manually trigger file replication from <Primary> to <Node 2> |  | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | for review | not required | not required | not required | not required
| Remove IIS server access restrictions |  |  | n/a | not required | to be completed | not required | not required | not required | not required
Smoke tests on <Node 2>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | not required | to be completed | not required | not required | not required | not required
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | not required | to be completed | not required | not required | not required | not required
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | not required | to be completed | not required | not required | not required | not required
| Start Asynchronous Request, Messaging, API and API SOAP services |  | To verify skins | n/a | not required | to be completed | not required | not required | not required | not required
| Verify that end users can authenticate |  |  | n/a | not required | to be completed | not required | not required | not required | not required
| Start Workflow Manager and Privileged Access Manager Service services |  | To verify workflow | n/a | not required | to be completed | not required | not required | not required | not required
| Verify requests to access a password - auto approved case |  |  | n/a | not required | to be completed | not required | not required | not required | not required
| Verify request to access a password - with authorization case | Workflow needs to remain on nodes sharing the same upgraded state (that is, same upgrade version) |  | n/a | not required | to be completed | not required | not required | not required | not required
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | to be completed | not required | not required | not required | not required
| Test connection to target systems |  |  | n/a | not required | to be completed | not required | not required | not required | not required
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | not required | for review | not required | not required | not required | not required
Adding back <Node 2>
| Remove access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
End node upgrade
Start node upgrade
Isolating <Node 3>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from upgrading node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. This includes blocking all ports used by Bravura Security Fabric services. | n/a | not required | not required | for review | not required | not required | not required
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See blue and purple box). |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Node 3>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | not required | not required | to be completed | not required | not required | not required
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | not required | not required | to be completed | not required | not required | not required
| Backup database on <Node 3> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | not required | not required | to be completed | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | not required | not required | for review | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | not required | not required | for review | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | not required | not required | for review | not required | not required | not required
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Do not proceed to the Post-Upgrade Tasks page | n/a | not required | not required | to be completed | not required | not required | not required
| Remove firewall between <Primary>, <Node 2> and <Node 3> | Firewalls should isolate upgraded nodes from non-upgraded/upgrading nodes (see Blue box) |  | n/a | for review | for review | for review | not required | not required | not required
| Complete Post-Upgrade Tasks |  | • Proceed to the Post-Upgrade Tasks • When complete remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | not required | to be completed | not required | not required | not required
| Manually rebuild skins if required |  | Required if rebuild skins fail or has issues during post-upgrade tasks | n/a | not required | not required | for review | not required | not required | not required
| Manually reload connector pack if required |  | Required if loading connectors fail or has issues during post-upgrade tasks Iddb required on the node this is ran on | n/a | not required | not required | for review | not required | not required | not required
| Manually reload components if required |  | Required if component initialization fails or has issues during upgrade script\manage_components.p load --upgrade Iddb required on the node this is ran on | n/a | not required | not required | for review | not required | not required | not required
| Manually trigger file replication from <Primary> to <Node 3> |  | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | not required | for review | not required | not required | not required
| Remove IIS server access restrictions |  |  | n/a | not required | not required | to be completed | not required | not required | not required
Smoke tests on <Node 3>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | not required | not required | to be completed | not required | not required | not required
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | not required | not required | to be completed | not required | not required | not required
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | not required | not required | to be completed | not required | not required | not required
| Start Asynchronous Request, Messaging, API and API SOAP services |  | To verify skins | n/a | not required | not required | to be completed | not required | not required | not required
| Verify that end users can authenticate |  |  | n/a | not required | not required | to be completed | not required | not required | not required
| Start Workflow Manager and Privileged Access Manager Service services |  | To verify workflow | n/a | not required | not required | to be completed | not required | not required | not required
| Verify requests to access a password - auto approved case |  |  | n/a | not required | not required | to be completed | not required | not required | not required
| Verify request to access a password - with authorization case | Workflow needs to remain on nodes sharing the same upgraded state (that is, same upgrade version) |  | n/a | not required | not required | to be completed | not required | not required | not required
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | not required | to be completed | not required | not required | not required
| Test connection to target systems |  |  | n/a | not required | not required | to be completed | not required | not required | not required
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | not required | not required | for review | not required | not required | not required
Adding back <Node 3>
| Remove access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
End node upgrade
Section to add more node upgrades
| Unhide sections between blue bars for each additional node required between 4 - 6. |  | Unhide columns I, J and K, and corresponding rows as required. | for review | n/a | n/a | n/a | n/a | n/a | n/a
| Add sections for nodes greater than 6. |  | Add rows between "Start node upgrade" to "End node upgrade" (between teal bars) for each additional node after Node 6. | for review | n/a | n/a | n/a | n/a | n/a | n/a
| Node 3 to Node n can be done in parallel as long as at least two other nodes have been successfully upgraded and are running in production. | Keep in mind upgraded nodes should always be isolated (e.g., via firewalls) from non-upgraded/upgrading nodes. | Modify rows corresponding on additional nodes if upgrading in parallel. They are currently configured for serial upgrades. | for review | n/a | n/a | n/a | n/a | n/a | n/a
Isolating <Node 4>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from upgrading node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. This includes blocking all ports used by Bravura Security Fabric services. | n/a | not required | not required | not required | for review | not required | not required
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See blue and purple box). |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Node 4>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | not required | not required | not required | to be completed | not required | not required
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | not required | not required | not required | to be completed | not required | not required
| Backup database on <Node 4> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | not required | not required | not required | to be completed | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | not required | not required | not required | for review | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | not required | not required | not required | for review | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | not required | not required | not required | for review | not required | not required
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Do not proceed to the Post-Upgrade Tasks page | n/a | not required | not required | not required | to be completed | not required | not required
| Remove firewalls between upgraded nodes. | Firewalls should isolate upgraded nodes from non-upgraded/upgrading nodes (see Blue box) |  | n/a | for review | for review | for review | for review | not required | not required
| Complete Post-Upgrade Tasks |  | • Proceed to the Post-Upgrade Tasks • When complete remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | not required | not required | to be completed | not required | not required
| Manually rebuild skins if required |  | Required if rebuild skins fail or has issues during post-upgrade tasks | n/a | not required | not required | not required | for review | not required | not required
| Manually reload connector pack if required |  | Required if loading connectors fail or has issues during post-upgrade tasks Iddb required on the node this is ran on | n/a | not required | not required | not required | for review | not required | not required
| Manually reload components if required |  | Required if component initialization fails or has issues during upgrade script\manage_components.p load --upgrade Iddb required on the node this is ran on | n/a | not required | not required | not required | for review | not required | not required
| Manually trigger file replication from <Primary> to <Node 4> |  | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | not required | not required | for review | not required | not required
| Remove IIS server access restrictions |  |  | n/a | not required | not required | not required | to be completed | not required | not required
Smoke tests on <Node 4>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | not required | not required | not required | to be completed | not required | not required
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | not required | not required | not required | to be completed | not required | not required
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | not required | not required | not required | to be completed | not required | not required
| Start Asynchronous Request, Messaging, API and API SOAP services |  | To verify skins | n/a | not required | not required | not required | to be completed | not required | not required
| End users can authenticate |  |  | n/a | not required | not required | not required | to be completed | not required | not required
| Start Workflow Manager and Privileged Access Manager Service services |  | To verify workflow | n/a | not required | not required | not required | to be completed | not required | not required
| Request to access a password - auto approved |  |  | n/a | not required | not required | not required | to be completed | not required | not required
| Request to access a password - with authorization | Workflow needs to remain on nodes sharing the same upgraded state (that is, same upgrade version) |  | n/a | not required | not required | not required | to be completed | not required | not required
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | not required | not required | to be completed | not required | not required
| Test connection to target systems |  |  | n/a | not required | not required | not required | to be completed | not required | not required
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | not required | not required | not required | for review | not required | not required
Adding back <Node 4>
| Remove access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Isolating <Node 5>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from upgrading node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. This includes blocking all ports used by Bravura Security Fabric services. | n/a | not required | not required | not required | not required | for review | not required
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See blue and purple box). |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Node 5>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | not required | not required | not required | not required | to be completed | not required
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | not required | not required | not required | not required | to be completed | not required
| Backup database on <Node 5> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | not required | not required | not required | not required | to be completed | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | not required | not required | not required | not required | for review | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | not required | not required | not required | not required | for review | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | not required | not required | not required | not required | for review | not required
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Do not proceed to the Post-Upgrade Tasks page | n/a | not required | not required | not required | not required | to be completed | not required
| Remove firewalls between upgraded nodes. | Firewalls should isolate upgraded nodes from non-upgraded/upgrading nodes (see Blue box) |  | n/a | for review | for review | for review | for review | for review | not required
| Complete Post-Upgrade Tasks |  | • Proceed to the Post-Upgrade Tasks • When complete remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | not required | not required | not required | to be completed | not required
| Manually rebuild skins if required |  | Required if rebuild skins fail or has issues during post-upgrade tasks | n/a | not required | not required | not required | not required | for review | not required
| Manually reload connector pack if required |  | Required if loading connectors fail or has issues during post-upgrade tasks Iddb required on the node this is ran on | n/a | not required | not required | not required | not required | for review | not required
| Manually reload components if required |  | Required if component initialization fails or has issues during upgrade script\manage_components.p load --upgrade Iddb required on the node this is ran on | n/a | not required | not required | not required | not required | for review | not required
| Manually trigger file replication from <Primary> to <Node 5> |  | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | not required | not required | not required | for review | not required
| Remove IIS server access restrictions |  |  | n/a | not required | not required | not required | not required | to be completed | not required
Smoke tests on <Node 5>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | not required | not required | not required | not required | to be completed | not required
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | not required | not required | not required | not required | to be completed | not required
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | not required | not required | not required | not required | to be completed | not required
| Start Asynchronous Request, Messaging, API and API SOAP services |  | To verify skins | n/a | not required | not required | not required | not required | to be completed | not required
| End users can authenticate |  |  | n/a | not required | not required | not required | not required | to be completed | not required
| Start Workflow Manager and Privileged Access Manager Service services |  | To verify workflow | n/a | not required | not required | not required | not required | to be completed | not required
| Request to access a password - auto approved |  |  | n/a | not required | not required | not required | not required | to be completed | not required
| Request to access a password - with authorization | Workflow needs to remain on nodes sharing the same upgraded state (that is, same upgrade version) |  | n/a | not required | not required | not required | not required | to be completed | not required
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | not required | not required | not required | to be completed | not required
| Test connection to target systems |  |  | n/a | not required | not required | not required | not required | to be completed | not required
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | not required | not required | not required | not required | for review | not required
Adding back <Node 5>
| Remove access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Isolating <Node 6>
| Restrict access via load balancer to upgrading node |  | Restrict all traffic to and from upgrading node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Configure firewalls to isolate upgrading node |  | For example, in Windows Firewall, configure rules to block Bravura Security Fabric outbound traffic from upgrading node to other nodes, and rules to block inbound Bravura Security Fabric traffic from other nodes to the upgrading node. This includes blocking all ports used by Bravura Security Fabric services. | n/a | not required | not required | not required | not required | not required | for review
| Ensure Bravura Security Fabric traffic is isolated between old version, upgraded and upgrading node. | Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. (See blue and purple box). |  | n/a | for review | for review | for review | for review | for review | for review
Upgrading <Node 6>
| Turn off IIS service |  | Restrict to localhost or disable completely. | n/a | not required | not required | not required | not required | not required | to be completed
| Backup the application node. (e.g. Incremental vm snapshot taken) |  |  | n/a | not required | not required | not required | not required | not required | to be completed
| Backup database on <Node 6> |  | • Via SQL Management Studio. • Alternatively using the installer method | n/a | not required | not required | not required | not required | not required | to be completed
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older |  | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. Details can be found here. | n/a | not required | not required | not required | not required | not required | for review
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only |  | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | not required | not required | not required | not required | not required | for review
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer |  | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade • If the CP is upgraded, and agents from newer connector packs are used in the solution, restore them now. If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | not required | not required | not required | not required | not required | for review
| Upgrade instance |  | • Run setup via installers • Select "Proceed with a rolling upgrade" • Do not proceed to the Post-Upgrade Tasks page | n/a | not required | not required | not required | not required | not required | to be completed
| Remove firewalls between upgraded nodes. | Firewalls should isolate upgraded nodes from non-upgraded/upgrading nodes (see Blue box) |  | n/a | for review | for review | for review | for review | for review | for review
| Complete Post-Upgrade Tasks |  | • Proceed to the Post-Upgrade Tasks • When complete remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | not required | not required | not required | not required | to be completed
| Manually rebuild skins if required |  | Required if rebuild skins fail or has issues during post-upgrade tasks | n/a | not required | not required | not required | not required | not required | for review
| Manually reload connector pack if required |  | Required if loading connectors fail or has issues during post-upgrade tasks Iddb required on the node this is ran on | n/a | not required | not required | not required | not required | not required | for review
| Manually reload components if required |  | Required if component initialization fails or has issues during upgrade script\manage_components.p load --upgrade Iddb required on the node this is ran on | n/a | not required | not required | not required | not required | not required | for review
| Manually trigger file replication from <Primary> to <Node 6> |  | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | not required | not required | not required | not required | for review
| Remove IIS server access restrictions |  |  | n/a | not required | not required | not required | not required | not required | to be completed
Smoke tests on <Node 6>
| Locate and collect setup logs |  | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | not required | not required | not required | not required | not required | to be completed
| Locate and collect upgrade logs |  | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | not required | not required | not required | not required | not required | to be completed
| Locate and collect idmsuite logs |  | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | not required | not required | not required | not required | not required | to be completed
| Start Asynchronous Request, Messaging, API and API SOAP services |  | To verify skins | n/a | not required | not required | not required | not required | not required | to be completed
| End users can authenticate |  |  | n/a | not required | not required | not required | not required | not required | to be completed
| Start Workflow Manager and Privileged Access Manager Service services |  | To verify workflow | n/a | not required | not required | not required | not required | not required | to be completed
| Request to access a password - auto approved |  |  | n/a | not required | not required | not required | not required | not required | to be completed
| Request to access a password - with authorization | Workflow needs to remain on nodes sharing the same upgraded state (that is, same upgrade version) |  | n/a | not required | not required | not required | not required | not required | to be completed
| Start the rest of Bravura Security Fabric services |  | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | not required | not required | not required | not required | to be completed
| Test connection to target systems |  |  | n/a | not required | not required | not required | not required | not required | to be completed
| Test plan use cases for smoke testing |  | Include additional test plan use cases to the smoke testing as needed | n/a | not required | not required | not required | not required | not required | for review
Adding back <Node 6>
| Remove access restrictions to upgraded node via load balancer | This step will put the upgraded node back into production. Any changes made on nodes of differing states will be delayed until all nodes are upgraded and thus on the same build version. | Remove all traffic restrictions to and from upgraded node | to be completed | n/a | n/a | n/a | n/a | n/a | n/a
| Confirm end users can access nodes from globally available URLs |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Finish node upgrades
Basic functionally tests
| Reenable password randomizations for all policies |  | Setting found on the "Managed system policies" page. More details can be found here. Setting will be replicated to secondary nodes. | n/a | to be completed | not required | not required | not required | not required | not required
| Randomize password |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Override password |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Confirm passwords are replicating between nodes |  | For example, compare password histories of a few accounts across all nodes. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Cleanup tasks
| Enable Bravura Security Fabric Scheduled tasks in the OS Scheduler |  |  | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Enable all schedule tasks related to Bravura Security Fabric services |  |  | n/a | for review | for review | for review | for review | for review | for review
| Enable OTP randomization |  | Set DisableAllOTP to 0 in the IDAPI directory of the instance registry key. | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
| Enable auto discovery on Primary node |  | Navigate to Scheduled jobs. Select PSUPDATE and enable. | n/a | to be completed | not required | not required | not required | not required | not required
| Disable RES_DISABLE_RANDOMIZATIONS_ALLOW_CHECKOUTS system variable |  | Disable this variable to disallow check-outs while randomization is disabled. Settings will be replicated to secondary nodes | n/a | to be completed | not required | not required | not required | not required | not required
| Review customizations |  | Confirm customizations pre-upgrade are configured and/or behaving as expected. | n/a | for review | for review | for review | for review | for review | for review
Follow up tests
| Test plan use cases |  | Run through test plan use cases | n/a | for review | for review | for review | for review | for review | for review
| Review system health and usage over the 3 days after upgrading is completed. |  | Add rows below to include any additional tests appropriate | n/a | to be completed | to be completed | to be completed | to be completed | to be completed | to be completed
Note on F5: Update with node IDs/names
Note on H5: Insert column for each node greater than 3 required, and add a corresponding section of rows noted between the blue bars.
Note on I5: Node 3 to Node n can be done in parallel as long as at least two other nodes have been successfully upgraded and are running in production.

## Hidden
Action status
fail
not required
partial pass
pass
skipped
for review
to be completed
optional
n/a