## Readme
Upgrade Playbook
An upgrade is where nodes are upgraded using the provided installer. This generally requires downtime.
Note: Review "Rolling Upgrade Playbook" to see if upgrading with minimal downtime is applicable.
An upgrade is appropriate for patch releases where major product changes such as schema changes are made.
An upgrade is appropriate for minor and major release upgrades.
This playbook is intended to be a step-by-step guide to walk through an upgrade systematically and safely.
This playbook is a:
starting template to modify with your organization's specific needs
checklist to prevent forgetting steps or running them out of order
record of decisions made both before and during upgrade
record of upgrade details, such as time taken on specific steps and outcomes
This playbook is not a:
replacement of the core docs, which should also be reviewed before upgrading
How to
1 | Review this playbook
Action status legend:
|  |  | fail | Step failed or could not be completed
|  |  | not required | Not required for this step on this node
|  |  | partial pass | Step passed but with minor issues or unexpected behavior
|  |  | pass | Step passed without issue
|  |  | skipped | Step can be skipped for this step on this node, add note as required
|  |  | for review | Review if this step is applicable to your organization and add any notes and/or details as required
|  |  | to be completed | Step needs to be completed
|  |  | optional | Step is optional
|  |  | n/a | This is not applicable
2 | Duplicate the "Upgrade Playbook - Queue Flush - master" sheet (to keep an original playbook), and modify the playbook copy for your specific use (rename it with the data and environment details where applicable)
| 2.1 | Update the node headings with your node IDs
| 2.2 | Add new columns for each additional node required beyond 3
| 2.3 | Primary node must be upgraded first, and completed before starting secondary nodes. We recommend keeping a minimum of two nodes running in production at all times. Assuming you have that, you can upgrade remaining nodes in parallel. If you want to do this, modify the playbook to reflect this.
| 2.4 | Include other specifics of your organization's setup, maintenance window and so on
|  | 2.4.1 | For rows marked as "for review", determine if they need to be completed, modify or marked with a different status (such as "to be completed" or "n/a").
|  | 2.4.2 | At your own risk, add new rows with steps to capture your organization's process requirements not otherwise included in this playbook.
Be careful that actions in new rows do not conflict with existing rows of the playbook.
|  | Note | Do not delete or hide any rows (except for hiding nodes you're not using).
Instead use the status fields and/or add notes.
3 | Duplicate your modified tab, run through the modified playbook in a test environment, and adjust as required
4 | Duplicate modified tab with any adjustments, upgrade production
5 | Fill in all columns of the sheet as you go through them (including timestamps and notes)
| 5.1 | Take appropriate notes as each step is completed
| 5.2 | For partial passes take notes as to what was unexpected and why it is still considered a pass
| 5.3 | If a step fails collect logs, record the current state (including product, environment and database) and snapshot if possible. This information will be required for troubleshooting.
Additional notes
Each line should be completed for all nodes before proceeding to the next line.
Do not delete any rows from the playbook, instead mark as "n/a" or such as applicable.
During the upgrading process, nodes are in one of three states - old version, upgrading and upgraded.
Playbook details
Playbook last reviewed | Reviewer | Versions verified | Tester | Release notes
2022-07-25 | CF | Upgraded from 12.2.5 to 12.4.0.34189 | CF | N/A
2022-11-24 | CF CT | N/A | N/A | N/A
2024-11-28 | CF | None | ML | Updates12.7 Upgrade

## Upgrade Playbook - Queue Flush
|  | Starting Version | Upgrade Version |  | Notes
Bravura Fabric
Bravura Connector Pack
All nodes in each line should be completed before proceeding to the next line. That is, ensure each node for a step is completed or otherwise addressed (such as, "not required") before proceeding to the next step. |  |  | Prod environment
Stage | Step | Explanation | System/Environment | Primary | Secondary 1 | Secondary 2 | Estimated time | Start time | End time | Notes
Preparation
| Create inventory of potentially affected systems | Have an inventory of potentially affected systems to determine the location of all Bravura Security Fabric components that need to be upgraded or migrated. A suggested list can be found here. | for review | not required | not required | not required
| Create a test plan | Have a test plan that identifies use cases covering the required capability of the system. More details can be found here. | for review | not required | not required | not required
| Verify os and sql server configuration | The windows operating system and database must be the same versions and configuration as existing nodes. This step simply asks people to verify this is indeed the case. | n/a | to be completed | to be completed | to be completed
| Verify system requirements | System requirements can be found here: • python version • Microsoft OLE DB Driver for SQL Server • .NET Core Hosting Bundle 6.0.x and Desktop Runtime 6.0.x • Supported database management systems | n/a | to be completed | to be completed | to be completed
| Verify product build version | Build version should match primary node's. Information for build version can be found here. | n/a | to be completed | to be completed | to be completed
| Check availability of database credentials | Need to make sure we have dba level access to all databases both to take backups and to apply the backups | n/a | to be completed | to be completed | to be completed
| Check availability to database backup locations | Need to make sure suitable space exists to hold the database backups. More details can be found here. | n/a | to be completed | to be completed | to be completed
| Check ability to transfer database backups to secondary sites | Need to ensure its known how the database backups will be transferred between the nodes. | n/a | to be completed | to be completed | to be completed
| Check availability of Bravura Security Fabric credentials | Need to make sure we have access to the Bravura Security Fabric service user credentials. More details can be found here. | n/a | to be completed | to be completed | to be completed
| Review release notes | Assess their impact on your deployment. Release notes can be found here. | to be completed | not required | not required | not required
| Check customizations | Confirm product customizations that will need to be ported. For example: • Scripts, plugins, and configuration files • Services • Reports • Product customizations and fixes • Web interface modifications • Language packs • Use "Instance customizations" report to discover customizations • Review previous changes to list all custom components | n/a | to be completed | not required | not required
| Determine if you have any customer-verified connectors | This step only applies when upgrading to CP 4.6.0 or newer Bravura Security-verified and Customer-verified connectors are listed here. | n/a | for review | for review | for review
| Determine if you have connectors that will be deprecated or removed during the Connector Pack upgrade | If you have connectors that are listed to be deprecated or removed please contact support. Removed connectors and replacements is listed here. | n/a | for review | for review | for review
| Check out administrator access as required | Ensure access to <ADMIN> accounts | n/a | to be completed | to be completed | to be completed
| Copy installation package to all servers |  | n/a | to be completed | to be completed | to be completed
| Confirm correct upgrade process is triggered | Verify the following option is available: • Perform a standard upgrade by flushing queue files beforehand (this may take some time) | n/a | for review | for review | for review
| Ensure pre-upgrade checks pass on each node | • Run setup • Select the products you want to upgrade • Bravura Security Fabric • Bravura Connector Pack 64-bit • Bravura Proxy Server • Ensure pre-upgrade tests pass • Cancel the installer | n/a | to be completed | to be completed | to be completed
| Estimate outage time | • Consider doing resync during low-usage time. • Work with DBA to take a compressed backup of your source node’s DB. Note how long it takes for the backup to complete. • Measure the time taken to copy that backup to each of the destination nodes | n/a | to be completed | to be completed | to be completed
Database upgrade dry run |  | This section is to walk through verifying the database upgrade can be completed smoothly.
| Create a back up of the Instance DB | The database upgrade test will be done against a copy of your database. This will help verify that the database can be upgraded without interferring with production. If errors occur during the database upgrade test they can be caught and handled before upgrading production. | n/a | for review | for review | for review
| Create a Test DB | Recommended to be done on a different server. The following is for MSSQL: 1. Log into SQL Server as a DBA 2. In "Database" create a new database | n/a | for review | for review | for review
| Apply database backup onto the Test DB | As DBA apply the database backup to the test database. Documentation on restoring SQL database can be found here. | n/a | for review | for review | for review
| Create DBUser Login for the Test DB | The following is for MSSQL: • Log into SQL Server as a DBA • In “Security → Logins”, create a new user. If SQL Server Authentication is selected ensure the options User must change password at next login and Enforce password expiration are deselected. | n/a | for review | for review | for review
| Give the DBUser permissions for the Test DB | The following is for MSSQL: Give the DBUser permissions on the Test DB • On SQL Server Management Studio, go to Security → Logins → right click the destination DBUser and select Properties. • On the General page ensure the test database is selected as "Default Database" • On the Server Roles page ensure the "public" server role is given. Ensure the "sysadmin" role is not given. • On the User mapping page ensure the user is mapped to the test database and the Default schema is set to the backed up schema. Check the following roles are given for the instance database: db_datareader, db_owner, db_datawriter, db_ddladmin, and public • On SQL Server Management Studio, go to Databases → (Test DB) → Users → right click the DBUser and select Properties. • On the Membership page verify the following roles are selected: db_datareader, db_owner, db_datawriter, and db_ddladmin | n/a | for review | for review | for review
| Run upgradetest.exe | upgradetest.exe -db <TestDB> -s <Server> -u <DBUser> Ensure the upgradetest.exe is from the installation package you are upgrading to. | n/a | for review | for review | for review
| Review results as needed | If there are any issues such as: • Failed upgrade scripts • Failed schema verification Please reach out to support. | n/a | for review | for review | for review
Upgrade
| Prepare custom component Upgrade | Dependent on the specific customization. For example, this step may include running custom Upgrade scripts, and/or removing custom components in favour of base product new features. | n/a | for review | not required | not required
| Enable RES_DISABLE_RANDOMIZATIONS_ALLOW_CHECKOUTS system variable | Enable this variable to allow check-outs while randomization is disabled. More details can be found here. Settings will be replicated to secondary nodes | n/a | to be completed | not required | not required
| Disable all password randomizations in all policies | Setting found on the "Managed system policies" page. More details can be found here. Setting will be replicated to secondary nodes. | n/a | to be completed | not required | not required
| Disable auto discovery | Navigate to Scheduled jobs. Select PSUPDATE and disable. | n/a | to be completed | not required | not required
| Ensure auto discovery is complete | Ensure that auto discovery has finished running and is no longer running. Do not kill the processes if they are running and just allow to complete. | n/a | to be completed | not required | not required
| Ensure no maintenance tasks scheduled on SQL nodes | Check with DBA to ensure that DB maintenance tasks, such as a DB reindex, will not be running during patching. | n/a | to be completed | to be completed | to be completed
| Disable Bravura Security Fabric Scheduled tasks in the OS Scheduler | Health checks, pwdconficts, etc. We need to ensure that pwdconflicts is not running until all nodes are operational otherwise it will identify a range of issues since the nodes are in a problematic state due to the database resynchronization being done. | n/a | to be completed | to be completed | to be completed
| Disable all schedule tasks related to Bravura Security Fabric services |  | n/a | for review | for review | for review
Enter system wide outage
| Restrict access via global load balancer and direct people to maintenance page |  | to be completed | not required | not required | not required
| Turn off IIS service | Restrict to localhost or disable completely. | n/a | to be completed | to be completed | to be completed
| Update components if required | This is step is only applicable if custom components need to be upgraded. | n/a | for review | for review | for review
| Upgrade proxy servers. | • Run setup via installers • Ensure IIS is off on each node after proxy server upgrade | to be completed | not required | not required | not required
| Upgrade connector pack on all nodes Upgrade to CP 4.5.x or older | This step is for Connector Packs that comes with Bravura Security Fabric versions 12.6.x or older. This step may not be necessary if no connector changes are made. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade Details can be found here. | n/a | for review | for review | for review
| Upgrade connector pack on all nodes Upgrade to CP 4.6.0 only | This step only applies when upgrading to Connector Pack 4.6.0. Please contact contact support@bravurasecurity.com. | n/a | for review | for review | for review
| Upgrade connector pack on all nodes Upgrade to CP 4.6.1 or newer | This step is for Connector Packs that come with Bravura Security Fabric versions 12.7.1 or newer. If custom connectors are used, they may need to be manually reloaded. • Run setup via installers • Ensure IIS is off on each node after connector pack upgrade If the pre-install check identifies any configured targets that are removed in the new Connector Pack version: • Check if there is a replacement • Determine a plan for these targets after the upgrade. Customer-verified connectors that are not used by configured targets are removed during upgrade from 4.5.x and below. Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). Note: If the IDM instance is not yet 12.7.1 or later, the Customer-Verified connectors will not yet be copied over in the post-install tasks. Details can be found here. | n/a | for review | for review | for review
| Start queue flush from Primary node | • Run setup via installers • Select "Perform a standard upgrade by flushing queue files beforehand (this may take some time)" • Complete pre install checks • Wait for the "Queue flush complete" confirmation | n/a | to be completed | not required | not required
| Incremental vm snapshot taken | Or generate back up. Note: Recommended state to have a back up as the queues are now empty | n/a | to be completed | to be completed | to be completed
| Upgrade primary instance | • Continue through installer screens • Remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: iddb and filerep services need to be running on the primary for post upgrade tasks to properly sync files on secondary nodes. Note: iddb and filerep services need to be running on the primary for post upgrade tasks to properly sync files on secondary nodes. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | to be completed | not required | not required
| Upgrade secondary instances | • Run setup via installers • Select "Perform a standard upgrade by flushing queue files beforehand (this may take some time)" • Remain on the Post-Upgrade Tasks page as continuing will turn services back on. Note: iddb and filerep services need to be running on the primary for post upgrade tasks to properly sync files on secondary nodes. Note: CP 4.6.1 or newer Customer-Verified connectors that are present for configured targets are copied from the provided zip file in the post-upgrade tasks when Loading connectors and when the main IDM instance is 12.7.1 or later (the loadcvagents.exe utility must be present for this action). | n/a | not required | to be completed | to be completed
| Turn services back on primary node. | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | to be completed | not required | not required
| Turn on IIS service | Remove IIS server access restrictions to localhost or re-enable completely. | n/a | to be completed | to be completed | to be completed
| Start up all services | Continue past the Post-Upgrade Tasks page and complete the usage of the installer. | n/a | not required | to be completed | to be completed
| Restart instance | This step only applies when upgrading from pre-12.5.0 to 12.5.0 or newer. Bravura Security Fabric has gone through rebranding and requires a restart of the instance after upgrade. | n/a | for review | for review | for review
| Add custom components |  | n/a | for review | not required | not required
| Manually rebuild skins if required NOTE: for secondary nodes, option to resynch files from primary. | Required only if rebuild skins fail or has issues during post-upgrade tasks | n/a | for review | for review | for review
| Manually reload connector pack if required | Required only if loading connectors fail or has issues during post-upgrade tasks | n/a | for review | for review | for review
| Manually reload components if required | Required only if component initialization fails or has issues during upgrade on script\manage_components.p load --Upgrade NOTE: idapi service is required for this step. | n/a | for review | not required | not required
| Test replication is working | For example, increment/decrement DEFAULT EXPIRY SECONDS value on one node and verify it gets propagated on other nodes | n/a | to be completed | to be completed | to be completed
| Verify database replication queues all report recent running of stored procedures being replicated recently | This can be verified from the primary to make sure all nodes are reporting as replicating with each other. | n/a | to be completed | not required | not required
| Trigger file replication from Primary to secondary nodes. | If any of the secondary nodes failed the "Finalizing replicated components and skins" post-upgrade task, from the primary node command line run this command: updinst.exe -syncreg -syncfile -serverid <serverid> NOTE: if the primary node in each instance has the CP installed as global (no agents in the instance's agent\ directory), add to the above the -globalcp option NOTE 2: this file replication may take longer ( an hour or two ) since it has to interrogate the entire state of the secondary node and this notably depends on network latency to check the file system state. | n/a | for review | not required | not required
| Enable access via global load balancer to the Primary node only | If this cannot be done, then the system wide outage would need to be extended until the secondaries can be added to the load balancer. | to be completed | not required | not required | not required
| Re-enable scheduled jobs in the product, except for PSUPDATE |  | n/a | to be completed | not required | not required
| Ensure correct nodes are doing password management. | Ensure the correct nodes continue to own managed system policies and drive randomization. NOTE: If any changes are required, do this after all nodes are replicating with each other so the primary is aware of the existence of the two secondary nodes via the servicelist table. | n/a | to be completed | not required | not required
| Reenable password randomizations for all policies | Setting found on the "Managed system policies" page. More details can be found here. Setting will be replicated to secondary nodes. | n/a | to be completed | not required | not required
| Disable RES_DISABLE_RANDOMIZATIONS_ALLOW_CHECKOUTS system variable | Disable this variable to disallow check-outs while randomization is disabled. Settings will be replicated to secondary nodes | n/a | to be completed | not required | not required
Leave outage - primary node
Smoke Tests
| Locate and collect setup logs | The setup.log file is located in Bravura Security Fabric installer source folder | n/a | to be completed | to be completed | to be completed
| Locate and collect upgrade logs | In setup.log file, search for variable name: HIDLOGFILE, upgrade log location is designated by this variable. The logs are usually named as <instancename>_upgrade.log | n/a | to be completed | to be completed | to be completed
| Locate and collect idmsuite logs | The idmsuite.log files are located in <Bravura security fabric instance name>\Logs More details here. | n/a | to be completed | to be completed | to be completed
| Test connection to target systems |  | n/a | to be completed | to be completed | to be completed
| End users can authenticate |  | n/a | to be completed | not required | not required
| Request to access a password - auto approved |  | n/a | to be completed | not required | not required
| Request to access a password - with authorization |  | n/a | to be completed | not required | not required
| Randomize password |  | n/a | to be completed | not required | not required
| Override password |  | n/a | to be completed | not required | not required
| Confirm passwords are replicating between secondary nodes and the primary |  | n/a | to be completed | not required | not required
| Test plan use cases for smoke testing | Include additional test plan use cases to the smoke testing as needed | n/a | for review | for review | for review
Allow Access
| Remove global load balancer restrictions |  | to be completed | not required | not required | not required
Leave system-wide outage
| Confirm end users can access from globally available URLs. |  | n/a | to be completed | to be completed | to be completed
Cleanup tasks
| Enable Bravura Security Fabric Scheduled tasks in the OS Scheduler |  | n/a | to be completed | to be completed | to be completed
| Enable auto discovery on Primary node | Navigate to Scheduled jobs. Select PSUPDATE and enable. | n/a | to be completed | not required | not required
Follow up tests
| Test plan use cases | Run through test plan use cases | n/a | for review | for review | for review
| Review log files from for the last 3 days including 12 hours of hours of usage from all 3 nodes to allow for health check of system operation | 24 hours after the maintenance activity, the last 3 days of logs so an assessment of the health of the system can be done. | n/a | to be completed | to be completed | to be completed

## Hidden
Action status
fail
not required
partial pass
pass
skipped
for review
to be completed
optional
n/a